## Sumary
Developer | Hours
Ruben | 1
Clifton | 1.75
Total: | 2.75
Project: | 300
297.25
Progress: | 1.739%
Tasks: | 69 | 17 | 69

## Task List
| Task | Estimate | Ruben | Clifton | Sub Tasks | Progress | Sub Task Tab
1 | Admin |  | 0 | 1.75 | 10 | 20% | Sub Task-Admin
2 | Main Appliction Design and Framework |  | 1 | 0 | 1 | 100% | Sub Task-Main Project Design
3 | Main DB |  | 0 | 0 | 3 | 0% | Sub Task-Main Database
4 | Clients |  | 0 | 0 | 28 | 0% | Sub Task-Client
5 | Client Types |  | 0 | 0 | 15 | 0% | Sub Task-Client Type
6 | Products |  | 0 | 0 | 1 | 0% | Sub Task-Template
7 | Subscription |  | 0 | 0 | 1 | 0% | Sub Task-Template
8 | Financials |  | 0 | 0 | 1 | 0% | Sub Task-Template
9 | Debit Orders - Not Linked To Anything |  | 0 | 0 | 1 | 0% | Sub Task-Template
10 | Queries |  | 0 | 0 | 1 | 0% | Sub Task-Template
11 | Telesales |  | 0 | 0 | 1 | 0% | Sub Task-Template
12 | SMS - Not linked to anything |  | 0 | 0 | 1 | 0% | Sub Task-Template
13 | Security |  | 0 | 0 | 1 | 0% | Sub Task-Template
14 | Reports |  | 0 | 0 | 1 | 0% | Sub Task-Template
15 | Business Processes |  | 0 | 0 | 1 | 0% | Sub Task-Template
16 | Obligtions |  | 0 | 0 | 1 | 0% | Sub Task-Template
17 | System |  | 0 | 0 | 1 | 0% | Sub Task-Template

## Sub Task-Admin
No | Description | Ruben | Clifton | Progress
1 | Create Git repository, set up source tree - Clifton PC |  | 0.25 | 100%
2 | Create project admin sheet |  | 1.5 | 100%
3 | Set up Git account - Ruben |  |  | 0%
4 | Set up Source tree - Ruben PC |  |  | 0%

## Sub Task-Main Project Design
No | Description | Ruben | Clifton | Progress
1 | Base obkect Identification | 1 | 0 | 100%

## Sub Task-Main Database
No | Description | Ruben | Clifton | Progress
1 | Create database | 0 | 0 | 0%
2 | Set up application security tables | 0 | 0 | 0%

## Sub Task-Template
No | Description | Ruben | Clifton | Progress
1 | Task Description | 0 | 0 | 0%

## Sub Task-Client
No | Description | Ruben | Clifton | Progress
1 | Client Table design | 0 | 0 | 0%
2 | Cliend data access models | 0 | 0 | 0%
3 | Client display models | 0 | 0 | 0%
4 | Client list view | 0 | 0 | 0%
5 | Client single view | 0 | 0 | 0%
6 | Client edit view | 0 | 0 | 0%
7 | Update Git | 0 | 0 | 0%

## Sub Task-Client Type
No | Description | Ruben | Clifton | Progress
1 | Client Type table design | 0 | 0 | 0%
2 | Clien Type data access models | 0 | 0 | 0%
3 | Client Type display models - Based on template to display any standard lookup | 0 | 0 | 0%
4 | Client Type list view and edit - Based on template to edit any standard lookup | 0 | 0 | 0%
5 | Update Git | 0 | 0 | 0%